CSE Senior Design Individual Status Report

**From**: Charles Beran (MAVS Systems)

**To**: Manfred Huber

**Date**: 7/15/2011

**Subject**: Status report for period 7/8/2011 through 7/14/2011

## Tasks Planned or Worked on This Period

| Task Id | Description of Work | Baseline Start | Actual Start | Planned Work | Value Earned (if complete) |
| --- | --- | --- | --- | --- | --- |
| Deliverable to Which Work Applied | Baseline Finish | Actual Finish | Actual Work |
| 1.4.3.4 | Updated Project Plan (weekly assignment) | 7/8/11 | 7/12/11 | 1 hr | 1 hr |
|  | 7/15/11 | 7/12/11 | .5 hrs |
| 1.1.3.1 | Charter Section Drafting | 7/3/11 | 7/5/11 | 1.75 hrs | 3 hrs |
|  | 7/14/11 | 7/7/11 | 3 hrs |
| 1.1.3.2 1.1.3.3 | Review of charter sections and formatting | 7/14/11 | 7/7/11 | 4 hrs | 4 hrs |
|  | 7/19/11 | 7/13/11 | 4 hrs |

**Explanation of work or schedule variances, if any:** We were ahead of schedule, so finished the charter earlier than expected.

## Work Planned for Next Period

| Task Id | Description of Work | Baseline Start | Actual Start | Planned Work | Value Earned (if complete) |
| --- | --- | --- | --- | --- | --- |
| Deliverable to Which Work Applied | Baseline Finish | Actual Finish | Actual Work |
| 1.4.3.5 | Project Plan Update | 7/15/11 | 7/15/11 | 1 hr |  |
|  | 7/21/11 |  |  |
| 1.2.1 | Architectural Design Draft and Review | 8/23/11 | 7/13/11 | 24 |  |
|  | 9/2/11 |  |  |
| 1\ |  |  |  |  |  |
|  |  |  |  |

## REFLECTION: Problems Encountered This Period

None; Everything has been going along smoothly.

## REFLECTION: Lessons Learned This Period *(continue on additional page, if necessary)*

Formatting was a lot easier, thanks to lessons learned in the SRD. Everything is still on track.