## Slide 1: MAVS SYSTEMS STATUS REPORT July 8, 2011
Captain Nate Beran
Lt. Karl Feinauer
Lt. Ivan Fan
Lt. Brian Shef
Lt. Hoang Tang
Notes: Ivan

## Slide 2: Overview
Team Accomplishments
Risk Management
Critical Issues/Resolutions
Upcoming Challenges
Key Deliverables
  SRD
  Project Plan
  Project Charter
Earned Value
Work Outlook
Notes: Ivan

## Slide 3: Team Accomplishments
SRD (DRAFT) Completion
  Submitted to sponsor and Professor for Initial Review
Project Plan (DRAFT) Completion
  Reviewed by Professor
Notes: Ivan

## Slide 4: Risk Management
Risk Management Officer
  Hoang Tang
Risk Management Plan
  Weekly assessment of upcoming risks, impacts, and possible mitigation strategy
Notes: Hoang

## Slide 5: Risk Management
RISK | PROBABILITY | IMPACT | EXPOSURE | MITIGATION
Team Members not available | .5 | 400 Hours | 200 Hours | Internal Deadlines that allow for some slip
Learning Curve Steeper than Previously Thought | .5 | 200 Hours | 100 Hours | Build Research into project Plan
Team Members Burned out | .6 | 300 Hours | 180 Hours | Monitor schedule and extend our internal deadline of necessary. Have some fun build into our schedule such as an upcoming pizza party
Notes: Hoang

## Slide 6: Critical Issues/Resolutions
Issue
  Did editing in google docs
  Upon porting into MS Word, formatting was mangled
  Restoring formatting took a lot longer than expected
  Brian upcoming Wedding and Honeymoon
Resolution
  Looking into sky drive to keep documents properly formatted while in draft stages
  Setting earlier internal deadlines to allow for possible formatting crisis
  Making sure meeting time correctly estimated
Notes: Brian

## Slide 7: Important Upcoming Tasks
July 19
  Project Charter (Draft)
  Project Plan (Draft)
July 21
  System Requirements Document (DRAFT)
July 28
  System Requirements Document (FINAL)
August 11
  Project Charter (Final)
  Project Plan (Final)
Notes: Brian

## Slide 8: SRD (DRAFT)
Requirements Elicitation – Complete
Individual Content Assignments – Complete
Individual Review – Complete
Team Review – Complete
Submission for Review - Complete
Awaiting Revision Suggestions
Notes: Karl

## Slide 9: Project Plan (DRAFT)
Senior Design 1 – Complete
Senior Design 2 (estimate) - Complete
Dependencies – Complete
Individual Review – Complete
Team Review – Complete
Submitted to Professor July 6th for Revision suggestions
Notes: Karl

## Slide 10: Charter (DRAFT)
Individual Assignments – 92 Complete
Individual Review – 15% Complete
Team Review – July 13 @ 6pm
Notes: Karl

## Slide 11: Earned Value
Task Name | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Work | BCWS (Labor) | ACWP (Labor) | BCWP (Labor) | Percent Complete | SPI (Labor) | CPI (Labor)
Senior Design I | 6/17/2011 | 7/19/2011 | 6/17/2011 | NA | 180.5 hrs | 88.37 hrs | 111.75 hrs | 164 hrs | 77.95 | 1.86 | 1.47
SRD | 6/17/2011 | 7/19/2011 | 6/17/2011 | NA | 116 hrs | 60 hrs | 89.25 hrs | 106 hrs | 80 | 1.77 | 1.19
Requirements Elicitation | 6/17/2011 | 7/3/2011 | 6/17/2011 | 7/3/2011 | 50 hrs | 50 hrs | 44 hrs | 50 hrs | 100 | 1 | 1.14
Initial Draft | 7/3/2011 | 7/15/2011 | 7/3/2011 | 7/5/2011 | 24 hrs | 10 hrs | 12.75 hrs | 24 hrs | 100 | 2.4 | 1.88
SRD Draft Review | 7/15/2011 | 7/17/2011 | 7/5/2011 | 7/6/2011 | 12 hrs | 0 hrs | 6 hrs | 12 hrs | 100 | 0 | 2
Final Review | 7/17/2011 | 7/17/2011 | 7/6/2011 | 7/6/2011 | 20 hrs | 0 hrs | 26.5 hrs | 20 hrs | 100 | 0 | 0.75
Requirements Draft Review Presentation | 7/17/2011 | 7/19/2011 | NA | NA | 10 hrs | 0 hrs | 0 hrs | 0 hrs | 0 | 0 | 0
Project Plan | 6/17/2011 | 7/19/2011 | 6/17/2011 | 7/6/2011 | 45 hrs | 22.3 hrs | 16 hrs | 45 hrs | 100 | 2.02 | 2.81
Learn MS Project | 6/17/2011 | 6/17/2011 | 6/17/2011 | 6/17/2011 | 10 hrs | 10 hrs | 5 hrs | 10 hrs | 100 | 1 | 2
Initial Draft SDI | 6/27/2011 | 7/15/2011 | 6/17/2011 | 7/4/2011 | 10 hrs | 6.15 hrs | 5 hrs | 10 hrs | 100 | 1.63 | 2
Initial Draft SDII | 6/27/2011 | 7/15/2011 | 6/17/2011 | 7/4/2011 | 10 hrs | 6.15 hrs | 2 hrs | 10 hrs | 100 | 1.63 | 5
Dependencies | 7/15/2011 | 7/19/2011 | 6/17/2011 | 7/4/2011 | 10 hrs | 0 hrs | 2 hrs | 10 hrs | 100 | 0 | 5
Final Review | 7/19/2011 | 7/19/2011 | 7/3/2011 | 7/6/2011 | 5 hrs | 0 hrs | 2 hrs | 5 hrs | 100 | 0 | 2.5
Project Charter | 7/3/2011 | 7/19/2011 | 7/5/2011 | NA | 19.5 hrs | 6.07 hrs | 6.5 hrs | 13 hrs | 53.85 | 2.14 | 2
Initial Draft | 7/3/2011 | 7/14/2011 | 7/5/2011 | NA | 13 hrs | 6.07 hrs | 6.5 hrs | 12 hrs | 92.31 | 1.98 | 1.85
Initial Draft Review | 7/14/2011 | 7/19/2011 | 7/7/2011 | NA | 6.5 hrs | 0 hrs | 0 hrs | 1 hr | 15.38 | 0 | 0
Notes: Nate

## Slide 12: Work Outlook
Finish Charter
  Individual Assignments
  Review
Revisions
  SRD
  Charter
  Project Plan
Weekly Tasks
  Presentation preparation
  Risk Management
Begin Looking at Architecture and Detail Design Documents
Research
Notes: Nate

## Slide 13: Questions?
Notes: Nate